## Plan_v1.0
FA24SE070-Green production & AI_Plan_v1.0
PROJECT TITLE |  | Green production & AI
PROJECT MANAGER |  | Bùi Thế Tâm
START DATE |  | 26/12/2023
NO. | MODULE |  | TASK OWNER | START DATE | DUE DATE | MD | TASK COMPLETE
|  | TASK | [5 empty] | NOTE 1
1 | Scope Of Work
2 | Requirement
2.1 | COLLECTION INFORMATION
2.1.1 | Business Analysis | 1.From the time of purchasing grapefruit seedlings (grafting) to the time of planting grapefruit seedlings | Thế Tâm | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.2 |  | 2. Taking care of grapefruit trees from the young stage until flowering | Phước Tấn | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.3 |  | 3. Taking care of grapefruit trees from flowering to fruiting | Phước Tấn | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.4 |  | 4. Grapefruit Harvesting | Thế Tâm | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.5 |  | 5. Managing the process of selling and exporting grapefruit | Quang Dũng | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.6 |  | 6. Grafting and selling seedlings (expansion) | Ái Giao | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.2 | REQUIREMENT ANALYSIS | [5 empty] | 100%
2.1.7 |  | Find functions related to Bussiness 1, 4 | Thế Tâm | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.8 |  | Find functions related to Bussiness 2 , 3 | Phước Tấn | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.9 |  | Find functions related to Bussiness 5 | Quang Dũng | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
2.1.10 |  | Find function related to Bussiness 6 | Ái Giao | 2024-12-25 16:00 | 2024-12-27 14:00 | 46 | 100%
3 | Analysis & Design
3.1 | DATABASE DESIGN
3.1.1 | ERD Conceptual | Thiết kế ERD dựa trên Requirement đã tìm hiểu | Ái Giao | 2024-12-28 09:00 | 2024-12-29 20:00 | 35 | 100%
|  |  | Phước Tấn |  |  |  | 100%
|  |  | Quang Dũng |  |  |  | 100%
|  |  | Thế Tâm |  |  |  | 100%
3.1.2 | ERD Logical | Thiết kế ERD dựa trên Requirement đã tìm hiểu | Ái Giao | 2024-12-29 09:00 | 2024-12-29 20:00 | 11 | 100%
|  |  | Phước Tấn |  |  |  | 100%
|  |  | Quang Dũng |  |  |  | 100%
|  |  | Thế Tâm |  |  |  | 100%
3.1.3 | ERD Conceptual | Thiết kế ERD dựa trên Requirement đã tìm hiểu | Ái Giao | 2024-12-30 09:00 | 2024-12-30 20:00 | 11 | 100%
|  |  | Phước Tấn |  |  |  | 100%
|  |  | Quang Dũng |  |  |  | 100%
|  |  | Thế Tâm |  |  |  | 100%
3.1.4 | Database Scriptable | Hình thành được Script SQL | Phước Tấn | 2024-12-30 20:30 | 2024-12-31 10:00 | 13.5 | 100%
3.2 | FRON-END
3.2.1 | UI/UX Design | figma drawing for web interface | Quang Dũng | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.2 |  | figma drawing for web interface | Ái Giao | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.3 |  | figma drawing for web interface | Thế Tâm | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.4 |  | figma drawing for web interface | Phước Tấn | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.5 | Responsive Design | Describes how the interface will adapt itself on different devices (PC, tablet, phone). | Ái Giao | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.6 | Framework or Library | Choose the tools or frameworks for front-end (ReactJS, , Bootstrap, etc.), make a note of them. | Quang Dũng | 2024-12-26 20:30 | 2025-01-05 20:30 | 240 | 0%
3.2.7 | Demo Map | Find a thirt party to intergrate an map can paint or circle in it | Quang Dũng | 2024-01-01 20:30 | 2024-01-05 20:30 | 96 | 0%
3.2.8 | [5 empty] | 0 | 0%
3.2.9 | [5 empty] | 0 | 0%
3.2.10 | [5 empty] | 0 | 0%
3.3 | BACK-END |  |  |  |  | 0
3.3.1 | System Architecture | Agree on the system architecture to use and the API standards | Phước Tấn | 2024-12-26 20:30 | 2025-01-02 20:30 | 168 | 0%
3.3.2 | Business Logic | Describe key business functions through use cases and requirements Difine all Role engage to system | Thế Tâm | 2024-12-26 20:30 | 2025-01-02 20:30 | 168 | 0%
3.3.3 | Framework or Library | Choose the tools or frameworks for back-end (.NET , AI Library, Google intergration, etc.), make a note of them. | Phước Tấn | 2024-12-26 20:30 | 2025-01-02 20:30 | 168 | 0%
3.3.4 | Demo AI intergration detect desease by picture | Find thirt party to intergrate AI to BE | Phước Tấn | 2024-01-01 20:30 | 2024-01-05 20:30 | 96 | 0%
3.3.5 | Demo AI intergration to chat about information of agricuture | Find thirt party to intergrate AI to BE | Thế Tâm | 2024-01-01 20:30 | 2024-01-05 20:30 | 96 | 0%
3.4 | MOBILE | [5 empty] | 0%
3.3.1 | Mobile UI/UX Design |  | Ái Giao | 2024-01-03 20:30 | 2024-01-06 08:30 | 60 | 0%
3.3.2 | Mobile UI/UX Design |  | Quang Dũng | 2024-01-03 20:30 | 2024-01-06 08:30 | 60 | 0%
3.3.3 | [5 empty] | 0 | 0%
3.3.10 | [5 empty] | 0 | 0%
4 | Building
4.1 | SETUP ENVIRONMENT (FRON-END/BACK-END/MOBILE/GITHUB/OTHER)
4.1.1 | Set Up Project GitHub | Chuẩn bị Repository trên Github và Invite tất cả thành viên | Thế Tâm | 2024-12-30 10:00 | 2024-12-31 10:00 | 24 | 100%
4.1.2 | Set Up Front-End project | Cấu hình project FE code | Ái Giao | 2024-12-30 10:00 | 2024-12-31 10:00 | 24 | 100%
4.1.3 | Set Up Back-End Project | Cấu hình project BE code | Thế Tâm | 2024-12-30 10:00 | 2025-01-02 10:00 | 72 | 100%
4.1.4 | Set Up Database Deployment |  | Phước Tấn | 2024-12-30 10:00 | 2025-01-02 10:00 | 72 | 100%
4.1.5 | CICD project BackEnd |  | Thế Tâm | 2024-12-30 10:00 | 2025-01-03 10:00 | 96 | 100%
4.1.6 |  |  |  | 2024-12-30 10:00 | 2024-12-31 10:00 | 24 | 0%
4.1.7 |  |  |  | 2024-12-30 10:00 | 2024-12-31 10:00 | 24 | 0%
4.1.8 | [5 empty] | 0 | 0%
4.2 | FRONT-END |  |  |  |  | 0
4.2.1 | [5 empty] | 0 | 0%
4.2.2 | [5 empty] | 0 | 0%
4.2.3 | [5 empty] | 0 | 0%
4.3 | BACK-END
4.3.1 | [5 empty] | 8 | 0%
4.4 | MOBILE
4.4.1
4.4.1.1 | [5 empty] | #NAME? | 0%
4.4.1.2 | [5 empty] | #NAME? | 0%
4.4.1.3 | [5 empty] | #NAME? | 0%
5 | Testing
5.1
5.2 | [5 empty] | 7 | 0%
5.3 | [5 empty] | 7 | 0%
5.4
5.5 | [5 empty] | 7 | 0%
5.6 | [5 empty] | 7 | 0%
5.7
6 | Document
6.1 | Report 1 | [5 empty] | 0%
6.2 | Report 2 | [5 empty] | 0%
6.3 | Report 3 | [5 empty] | 0%
6.4 | Report 4 | [5 empty] | 0%
6.5 | Report 5 | [5 empty] | 0%
6.6 | Report 6 | [5 empty] | 0%
6.7 | Final report | [5 empty] | 0%
6.8 | User guide | [5 empty] | 0%
7 | Deployment
7.1 | Database | [5 empty] | 0%
7.2 | Front-end | [5 empty] | 0%
7.3 | Back-end | [5 empty] | 0%

## Contribution Work
R&D
Thành viên nhóm | Khối lượng công việc được giao | Hoàn thành
Bùi Thế Tâm | 25% | 100%
Lưu Ái Giao | 25%
Lê Quang Dũng | 25%
Huỳnh Phước Tấn | 25%
DOCUMENT
Thành viên nhóm | Khối lượng công việc được giao | Hoàn thành
Bùi Thế Tâm | 25% | 100%
Lưu Ái Giao | 25%
Lê Quang Dũng | 25%
Huỳnh Phước Tấn | 25%
TESTING
Thành viên nhóm | Khối lượng công việc được giao | Hoàn thành
Bùi Thế Tâm | 25% | 100%
Lưu Ái Giao | 25%
Lê Quang Dũng | 25%
Huỳnh Phước Tấn | 25%